## Возможные риски
Возможные риски (Идентификация рисков):
Проект:
Возможный риск | Проблема/Риск | Действие
Списко всех возможных рисков (интервью, brainstorming, база знаний). | Определить, что это проблема, ограничение (П) или риск (Р) | Определить соответствующее действие для каждого определяемого элемента П в предыдущей колонке. Потенциал действия включают "консолидировать", "нагнетать", повторить", "выходящее за пределы проекта", или определить как риск и изменить обозначение в предыдущей колонке на Р.

## Классификация рисков
Классификация рисков:
Проект:
Possible Risks | Identification Number | Classification / Category | Conditions | Consequences
Place the "R" designated items from the Possible Risks worksheet here. | Use a number to uniquely identify each risk. | • People - Customer - End User - Sponsors - Stakeholders - Personnel - Organization - Skills - Politics - Morale • Process - Mission and Goals - Decision Making - Project Characteristics - Budget, Costs, and Schedules - Requirements - Designs - Building - Testing • Technology - Security - Development and Test Environment - Tools - Deployment - Support - Operational Environment - Availability • Environmental - Legal - Regulatory - Competition - Economic - Technology - Business | Identify the cause of the risk. | Define the potential result of the risk. There may be multiple consequences for each condition. Some consequences can also be conditions.

## Анализ и приоритезация рисков
Анализ и приоритезация рисков
Проект:
ID Number | Priority / Order | Probability (Numeric) | Impact (Numeric) | Exposure (Numeric) | Exposure Recipient (Text)
|  | Likelihood of the Risk Condition occurring, with 1% - 30% for low, 31% - 70% for medium, and 71% - 100% for high | Effect of the Risk Consequence, with 1 - 3 for low; 4 - 7 for medium, 8 - 10 for high, and 100 for catastrophic ratings | Calculated by multiplying Risk Probability times Risk Impact, and used as the basis for ordering and prioritizing Risks | Identify who will be affected by the risk exposure (e.g., Client, Partner, & Microsoft).

## Планирование рисков
Risk Planning - (Use For Risk Costing)
Organization:
Initiative, Project, and/or Engagement:
Date:
ID Number | Priority / Order | Mitigation Plans | Contingency Plans | Triggers | Responsible Person | Deliverables | Activities And Tasks | Dependencies | Time Frames | Due Dates | Resource Requirements
|  | Identify what must be done to reduce the probability of the risk condition occurring. | Identify what must be done to reduce the impact of the risk consequence. | Identify the criteria for determining when to initiate risk contingency plans. | Identify the person responsible for each risk plan. | Identify the deliverables that will be created by each risk plan. | Identify the tasks and associated activities that will create the deliverables for each risk plan. | Identify the tasks/activities that are dependent upon each other within each risk plan. | Identify the start and complete dates for each risk plan. | Identify the due date for each deliverable of the risk plan. | Identify the skills, person hours, equipment, facilities, hardware, software and other resources needed for each deliverable of the risk plan. (Enter each as individual and separate line items)

## Затраты
Risk Costing
Organization:
Initiative, Project, and/or Engagement:
Date:
ID Number | Priority / Order | Resource Requirements | Resource Unit Cost | Resource Total Cost | Risk Plan Total Cost | Margin | Preferred Price | Competition Anticipated Price | Customer Anticipate Price | Proposed Price
|  | Identify the skills, person hours, equipment, facilities, hardware, software and other resources needed for each deliverable of the risk plan (enter as individual and separate line items) | The actual or estimated unit cost for each of the individual resource requirement line items | Calculate the total cost for each resource requirement line item. Multiply each individual resource requirement by its associated unit cost | Calculate the estimated total cost for implementing each risk plan. Add all resource total costs for each resource unit cost line item | Identify the desired return on investment for each risk plan, expressed as a percentage | Calculate the favored price to the customer in taking responsibility for and implementing each risk plan. Multiplying the margin percentage by the total cost for each risk plan and add the results to the total cost of each risk plan | Identify what competitors would charge the customer if they took responsibility for and implemented each risk plan | Estimate what the customer would consider an acceptable price for implementing each risk plan | Identify the price to be submitted to the customer to take responsibility for and implement each risk plan. Balance among the preferred price, competitive anticipated price, and customer anticipated price